## Backend
Payroll Management System - Project Plan
Workstream: Backend Development ¦ Owners: Backend Team, Project Team ¦ Modules: Reimbursement Management, Employee Deduction Management
Tasks: 49 Reporting date: 10-Aug-2026 ¦ Delivery: 21-Aug-2026
Task/Activity | Activity Details | Status | No of Days | Start | Finish | Dependency | Owner | Scope
PHASE 1. Requirements & Analysis
BE-01 - Requirement study - Reimbursement module | Study the approved business requirement for employee reimbursement submission and administrator review. Record assumptions, open questions and out-of-scope items. |  |  |  |  | - | Backend Team | Reimbursement Module
PM-01 - Project kick-off | Hold the kick-off with all teams and the business owner, confirming objectives, scope boundaries and ways of working. |  |  |  |  | - | Project Team | Common Platform Activities
PM-02 - Scope baseline and exclusions register | Baseline the agreed scope for both modules and record explicit exclusions, including payroll processing changes deferred to a future release. |  |  |  |  | PM-01 | Project Team | Common Platform Activities
BE-02 - Requirement study - Deduction module | Study the approved business requirement for administrator-initiated employee deductions. Confirm the reason categories in scope and clarify recovery expectations. |  |  |  |  | BE-01 | Backend Team | Deduction Module
BE-03 - Backend effort estimation and task breakdown | Break both modules into backend work packages, size the effort in days and agree the delivery sequence with the project manager. |  |  |  |  | BE-01, BE-02 | Backend Team | Common Platform Activities
BE-04 - Requirement clarification and sign-off | Close all open requirement questions with the business owner and obtain written confirmation of scope for both modules. |  |  |  |  | BE-03 | Project Team | Common Platform Activities
PM-03 - Consolidated project plan and baseline | Consolidate backend, frontend, integration and testing estimates into the baselined project plan with the agreed delivery date. |  |  |  |  | BE-03, FE-03, QA-01 | Project Team | Common Platform Activities
BE-05 - Backend solution approach review | Review the proposed backend approach for both modules with the technical lead. Record agreed decisions, risks and alignment with existing platform conventions. |  |  |  |  | BE-04 | Backend Team | Common Platform Activities
BE-06 - Reimbursement information model sign-off | Agree what information the system must retain for a reimbursement request, its attachments and its approval outcome, including the partially approved amount. |  |  |  |  | BE-05 | Backend Team | Reimbursement Module
BE-07 - Deduction information model sign-off | Agree what information the system must retain for an employee deduction record, including deduction month, reason and status. |  |  |  |  | BE-05 | Backend Team | Deduction Module
PM-07 - Weekly status reporting | Prepare and circulate the weekly status report covering progress, effort consumed, risks and decisions required. |  |  |  |  | PM-06 | Project Team | Common Platform Activities
PHASE 3. Development
BE-08 - Reimbursement type configuration capability | Build the ability to maintain the list of reimbursement types available to employees within an organization, including active and inactive handling. |  |  |  |  | BE-06 | Backend Team | Reimbursement Module
BE-22 - Deduction creation capability | Build the administrator capability to raise a deduction against an employee capturing amount, deduction month, reason and remarks. |  |  |  |  | BE-07 | Backend Team | Deduction Module
BE-23 - Deduction reason configuration | Maintain the selectable deduction reasons covering asset damage, salary advance recovery, loan recovery and notice period recovery. |  |  |  |  | BE-07 | Backend Team | Deduction Module
PM-08 - Requirement change control | Assess any change requests raised during delivery for impact on scope, effort and the delivery date, and obtain approval before acceptance. |  |  |  |  | PM-02 | Project Team | Common Platform Activities
BE-09 - Reimbursement request submission capability | Build the server-side capability for an employee to raise a reimbursement request capturing type, requested amount, bill date, description and supporting attachment. |  |  |  |  | BE-08 | Backend Team | Reimbursement Module
BE-24 - Deduction creation validation rules | Implement checks on deduction amount, deduction month and prevention of duplicate deductions for the same employee and period. |  |  |  |  | BE-22, BE-23 | Backend Team | Deduction Module
BE-25 - Employee lookup for deduction entry | Provide employee search to support deduction entry, limited to active employees of the requesting organization. |  |  |  |  | BE-22 | Backend Team | Deduction Module
BE-26 - Deduction listing capability | Provide the administrator list of recorded deductions for the active organization with summary values. |  |  |  |  | BE-22 | Backend Team | Deduction Module
BE-10 - Reimbursement submission validation rules | Implement the business rule checks applied on submission, covering mandatory fields, permitted amount range, bill date validity and duplicate submission control. |  |  |  |  | BE-09 | Backend Team | Reimbursement Module
BE-11 - Attachment management capability | Enable supporting bills to be attached, retrieved and removed against a request, with file type and size restrictions applied. |  |  |  |  | BE-09 | Backend Team | Reimbursement Module
BE-12 - Employee reimbursement history retrieval | Provide the employee-facing view of previously raised requests showing current status, requested amount and approved outcome. |  |  |  |  | BE-09 | Backend Team | Reimbursement Module
BE-27 - Deduction update capability | Allow an existing deduction to be amended while it remains eligible for change. |  |  |  |  | BE-26 | Backend Team | Deduction Module
BE-29 - Deduction filtering and search | Enable deductions to be filtered by employee, reason, deduction month and status. |  |  |  |  | BE-26 | Backend Team | Deduction Module
BE-13 - Administrator pending reimbursement list | Provide the administrator view of reimbursement requests awaiting review for the active organization, ordered for efficient processing. |  |  |  |  | BE-12 | Backend Team | Reimbursement Module
BE-28 - Deduction removal capability | Allow a deduction record to be withdrawn, retaining history rather than removing the record permanently. |  |  |  |  | BE-27 | Backend Team | Deduction Module
BE-30 - Deduction status management | Maintain the status of each deduction record through its lifecycle and prevent changes once it has been finalised. |  |  |  |  | BE-27 | Backend Team | Deduction Module
BE-14 - Reimbursement detail retrieval for review | Provide the complete request detail an approver needs, including attachments, submission date and prior remarks. |  |  |  |  | BE-13 | Backend Team | Reimbursement Module
BE-19 - Reimbursement search and filtering | Enable reimbursement records to be filtered by employee, type, status, submission date range and amount range. |  |  |  |  | BE-13 | Backend Team | Reimbursement Module
BE-31 - Deduction history reporting data | Provide the consolidated deduction history required for administrator reporting and audit review. |  |  |  |  | BE-29, BE-30 | Backend Team | Deduction Module
BE-15 - Reimbursement approval workflow | Build the approval action, recording the approver, approval date and resulting status transition. |  |  |  |  | BE-14 | Backend Team | Reimbursement Module
BE-32 - Organization-level data access enforcement | Ensure every record in both modules is restricted to the requesting organization, consistent with existing platform behaviour. |  |  |  |  | BE-13, BE-26 | Backend Team | Common Platform Activities
BE-35 - Backend peer review - Deduction module | Peer review the deduction backend work packages against the agreed approach and platform conventions. Log and close review observations. |  |  |  |  | BE-31 | Backend Team | Deduction Module
BE-16 - Reimbursement partial approval handling | Support recording an approved amount lower than the requested amount, retaining both values so the variance remains visible for reporting. |  |  |  |  | BE-15 | Backend Team | Reimbursement Module
BE-17 - Reimbursement rejection workflow | Build the rejection action with mandatory reason capture and the associated status transition. |  |  |  |  | BE-15 | Backend Team | Reimbursement Module
PM-11 - Milestone review - deduction development complete | Review and confirm completion of deduction module development across backend and frontend. |  |  |  |  | BE-31, FE-30 | Project Team | Common Platform Activities
BE-33 - Portal and role access enforcement | Confirm employee-facing and administrator-facing capabilities are exposed only to the correct portal audience. |  |  |  |  | BE-32 | Backend Team | Common Platform Activities
BE-18 - Reimbursement remarks management | Allow approvers to capture and revise remarks against a request without altering the approved amount. |  |  |  |  | BE-16, BE-17 | Backend Team | Reimbursement Module
BE-20 - Reimbursement status lifecycle controls | Enforce the permitted status transitions and prevent further changes to requests that have been finalised. |  |  |  |  | BE-18 | Backend Team | Reimbursement Module
BE-21 - Approved amount availability for downstream payroll use | Make the approved reimbursement amount available in a consumable form for a future payroll cycle. No payroll processing changes are included in this scope. |  |  |  |  | BE-20 | Backend Team | Reimbursement Module
BE-34 - Backend peer review - Reimbursement module | Peer review the reimbursement backend work packages against the agreed approach and platform conventions. Log and close review observations. |  |  |  |  | BE-21 | Backend Team | Reimbursement Module
PM-10 - Milestone review - reimbursement development complete | Review and confirm completion of reimbursement module development across backend and frontend. |  |  |  |  | BE-21, FE-21 | Project Team | Common Platform Activities
BE-36 - Backend verification pass before handover | Complete developer-level verification of both modules and record the outcome before handover to the integration and QA teams. |  |  |  |  | BE-34, BE-35 | Backend Team | Common Platform Activities
BE-37 - Backend handover documentation | Produce backend handover notes covering module behaviour, configuration points, assumptions and known limitations. |  |  |  |  | BE-36 | Backend Team | Common Platform Activities
PHASE 6. Defect Resolution
BE-40 - Payroll consumption impact assessment | Assess what would be required to consume approved reimbursement and deduction amounts in a future payroll cycle. Planning input only, no build activity in this release. |  |  |  |  | BE-21 | Backend Team | Reimbursement Module
BE-38 - Backend defect resolution - cycle 1 | Resolve backend defects raised during functional and service-level testing of both modules. Re-verify each fix before returning it to the QA team. |  |  |  |  | QA-28 | Backend Team | Common Platform Activities
BE-39 - Backend defect resolution - cycle 2 | Resolve remaining and regression-related backend defects and confirm no impact on existing payroll behaviour. |  |  |  |  | BE-38 | Backend Team | Common Platform Activities
PHASE 7. UAT
BE-41 - Backend UAT support | Support business users during user acceptance testing, investigate reported queries and provide clarifications. |  |  |  |  | QA-34 | Backend Team | Common Platform Activities
PHASE 8. Release & Closure
BE-42 - Backend release verification | Complete final backend verification against the release checklist and confirm readiness for production deployment. |  |  |  |  | BE-41 | Backend Team | Common Platform Activities
TOTAL | 49 tasks

## Frontend
Payroll Management System - Project Plan
Workstream: Frontend Development ¦ Owners: Frontend Team, Project Team ¦ Portals: Employee Portal, Administrator Portal
Tasks: 42 ¦ Reporting date: 10-Aug-2026 ¦ Delivery: 21-Aug-2026
Task/Activity | Activity Details | Status | No of Days | Start | Finish | Dependency | Owner | Scope
PHASE 1. Requirements & Analysis
FE-01 - User interface requirement walkthrough | Walk through the approved requirement for both modules from a user experience perspective and confirm the screens in scope. |  |  |  |  | - | Frontend Team | Common Platform Activities
FE-02 - Screen inventory and navigation plan | List every screen required for the employee portal and administrator portal, and agree how each is reached from existing navigation. |  |  |  |  | FE-01 | Frontend Team | Common Platform Activities
FE-03 - Frontend effort estimation and breakdown | Break the screen inventory into frontend work packages, size the effort in days and agree the build sequence. |  |  |  |  | FE-02 | Frontend Team | Common Platform Activities
PM-04 - Resource allocation and RACI | Confirm team allocation across both modules and agree responsibilities for each phase. |  |  |  |  | PM-03 | Project Team | Common Platform Activities
PHASE 2. Design & Planning
FE-04 - Screen design review with business | Review the proposed screen flows and field layouts with the business owner and obtain confirmation before build begins. |  |  |  |  | FE-03 | Project Team | Common Platform Activities
FE-05 - Reusable form and list pattern alignment | Confirm the shared form, list, filter and notification patterns to be reused so both modules remain consistent with the existing application. |  |  |  |  | FE-04 | Frontend Team | Common Platform Activities
PM-09 - Milestone review - design sign-off | Review and formally confirm completion of the design and planning phase for both modules. |  |  |  |  | BE-07, FE-05, QA-01 | Project Team | Common Platform Activities
PM-06 - Communication and reporting plan | Agree the reporting cadence, status report format and escalation path with the business owner. |  |  |  |  | PM-04 | Project Team | Common Platform Activities
PHASE 3. Development
FE-06 - Employee reimbursement request form | Build the employee-facing request form capturing reimbursement type, requested amount, bill date, description and attachment. |  |  |  |  | FE-05 | Frontend Team | Reimbursement Module
FE-22 - Administrator deduction creation screen | Build the administrator screen to raise a deduction capturing employee, amount, deduction month, reason and remarks. |  |  |  |  | FE-05 | Frontend Team | Deduction Module
FE-07 - Reimbursement form validation behaviour | Apply field-level validation and user messaging on the request form, covering mandatory fields, amount format and bill date rules. |  |  |  |  | FE-06 | Frontend Team | Reimbursement Module
FE-08 - Reimbursement type selection behaviour | Present the available reimbursement types and apply any type-specific guidance or limits shown to the employee. |  |  |  |  | FE-06 | Frontend Team | Reimbursement Module
FE-09 - Attachment upload experience | Build the attachment upload experience including progress indication, permitted file guidance and error messaging. |  |  |  |  | FE-06 | Frontend Team | Reimbursement Module
FE-12 - Employee reimbursement history screen | Build the employee history screen listing previously raised requests with requested and approved amounts. |  |  |  |  | FE-05 | Frontend Team | Reimbursement Module
FE-23 - Employee selection experience for deductions | Provide employee search and selection on the deduction screen, restricted to active employees. |  |  |  |  | FE-22 | Frontend Team | Deduction Module
FE-24 - Deduction form validation behaviour | Apply field-level validation and user messaging on the deduction form, covering mandatory fields and amount format. |  |  |  |  | FE-22 | Frontend Team | Deduction Module
FE-25 - Deduction month selection behaviour | Provide deduction month selection with the permitted range applied and clear guidance to the administrator. |  |  |  |  | FE-22 | Frontend Team | Deduction Module
FE-26 - Deduction listing screen | Build the administrator list of recorded deductions with the summary information required for review. |  |  |  |  | FE-22 | Frontend Team | Deduction Module
FE-10 - Attachment preview and removal experience | Allow an employee to review an attached bill and remove it before the request is submitted. |  |  |  |  | FE-09 | Frontend Team | Reimbursement Module
FE-11 - Reimbursement submission confirmation experience | Provide clear confirmation, failure handling and navigation once a request has been submitted. |  |  |  |  | FE-07 | Frontend Team | Reimbursement Module
FE-15 - Administrator pending reimbursement list screen | Build the administrator list of reimbursement requests awaiting review, with the summary information needed to prioritise. |  |  |  |  | FE-05 | Frontend Team | Reimbursement Module
FE-13 - Reimbursement history status presentation | Present request status clearly, including the partially approved case where the approved amount differs from the requested amount. |  |  |  |  | FE-12 | Frontend Team | Reimbursement Module
FE-14 - Reimbursement history filtering controls | Provide the employee with filtering by status, reimbursement type and date range on the history screen. |  |  |  |  | FE-12 | Frontend Team | Reimbursement Module
FE-27 - Deduction list filtering controls | Provide filtering by employee, reason, deduction month and status on the deduction list. |  |  |  |  | FE-26 | Frontend Team | Deduction Module
FE-28 - Deduction edit experience | Allow an administrator to amend an existing deduction, with fields locked once the record is no longer eligible for change. |  |  |  |  | FE-26 | Frontend Team | Deduction Module
FE-16 - Reimbursement list search and filter controls | Provide administrator search and filtering by employee, type, status, date range and amount range. |  |  |  |  | FE-15 | Frontend Team | Reimbursement Module
FE-17 - Reimbursement detail review screen | Build the review screen presenting full request detail, attachments and prior remarks to the approver. |  |  |  |  | FE-15 | Frontend Team | Reimbursement Module
FE-29 - Deduction removal confirmation experience | Provide a confirmation step before a deduction is withdrawn, with clear feedback on the outcome. |  |  |  |  | FE-28 | Frontend Team | Deduction Module
FE-30 - Deduction history view | Build the deduction history view supporting administrator review and audit queries. |  |  |  |  | FE-26 | Frontend Team | Deduction Module
FE-18 - Approval action experience | Build the approval action with confirmation handling and clear feedback to the approver. |  |  |  |  | FE-17 | Frontend Team | Reimbursement Module
FE-20 - Rejection action experience | Build the rejection action with mandatory reason capture and confirmation handling. |  |  |  |  | FE-17 | Frontend Team | Reimbursement Module
FE-31 - Portal access behaviour for new screens | Ensure employee screens appear only in the employee portal and administrator screens only in the administrator portal, following existing route protection. |  |  |  |  | FE-12, FE-15, FE-22 | Frontend Team | Common Platform Activities
FE-33 - Frontend peer review - Deduction screens | Peer review the deduction screens against the agreed designs and application conventions. Log and close review observations. |  |  |  |  | FE-30 | Frontend Team | Deduction Module
FE-19 - Partial approval amount entry experience | Allow the approver to enter an approved amount lower than the requested amount, with validation preventing an amount above the request. |  |  |  |  | FE-18 | Frontend Team | Reimbursement Module
FE-21 - Remarks capture experience | Allow the approver to record and revise remarks against a request from the review screen. |  |  |  |  | FE-19, FE-20 | Frontend Team | Reimbursement Module
FE-32 - Frontend peer review - Reimbursement screens | Peer review the reimbursement screens against the agreed designs and application conventions. Log and close review observations. |  |  |  |  | FE-21 | Frontend Team | Reimbursement Module
FE-34 - Cross-browser and responsive review | Verify both modules behave correctly across supported browsers and screen sizes, including the mobile presentation of list screens. |  |  |  |  | FE-32, FE-33 | Frontend Team | Common Platform Activities
FE-35 - Frontend documentation and handover notes | Produce screen-level handover notes covering navigation, validation behaviour and known limitations. |  |  |  |  | FE-34 | Frontend Team | Common Platform Activities
PHASE 6. Defect Resolution
FE-36 - Frontend defect resolution - cycle 1 | Resolve frontend defects raised during functional and validation testing of both modules. Re-verify each fix before returning it to the QA team. |  |  |  |  | QA-28 | Frontend Team | Common Platform Activities
FE-37 - Frontend defect resolution - cycle 2 | Resolve remaining and regression-related frontend defects across both modules. |  |  |  |  | FE-36 | Frontend Team | Common Platform Activities
PHASE 7. UAT
FE-38 - Frontend UAT support | Support business users during user acceptance testing, reproduce reported issues and provide clarifications. |  |  |  |  | QA-34 | Frontend Team | Common Platform Activities
PHASE 8. Release & Closure
FE-39 - Frontend release verification | Complete final frontend verification against the release checklist and confirm readiness for production deployment. |  |  |  |  | FE-38 | Frontend Team | Common Platform Activities
TOTAL | 42 tasks

## Integration
Payroll Management System - Project Plan
Workstream: Integration and Release ¦ Owners: Integration Team, Project Team ¦ End-to-end wiring, environment readiness, deployment and go-live
Tasks: 41 ¦ Reporting date: 10-Aug-2026 ¦ Delivery: 21-Aug-2026
Task/Activity | Activity Details | Status | No of Days | Start | Finish | Dependency | Owner | Scope
PHASE 2. Design & Planning
IN-01 - Integration approach alignment | Agree how both modules will be integrated end to end, the sequence of integration slices and the entry criteria for each slice. |  |  |  |  | BE-05, FE-05 | Integration Team | Common Platform Activities
IN-02 - Integration environment readiness | Confirm the shared development and non-production environments are available and correctly configured for integration activity. |  |  |  |  | IN-01 | Integration Team | Common Platform Activities
IN-03 - Cross-team handover checkpoints | Agree the handover checkpoints between the backend and frontend teams so each integration slice can begin without rework. |  |  |  |  | IN-01 | Integration Team | Common Platform Activities
PM-05 - Risk and issue register setup | Establish the risk and issue register with initial entries, owners and mitigation actions. |  |  |  |  | PM-03 | Project Team | Common Platform Activities
PHASE 4. Integration
IN-04 - Reimbursement submission end-to-end wiring | Connect the employee request form to the backend submission capability and confirm a request can be raised successfully end to end. |  |  |  |  | BE-09, FE-06 | Integration Team | Reimbursement Module
IN-16 - Deduction creation end-to-end wiring | Connect the deduction creation screen to the backend creation capability and confirm a deduction can be raised end to end. |  |  |  |  | BE-22, FE-22 | Integration Team | Deduction Module
IN-05 - Reimbursement validation handling end-to-end | Confirm business rule failures raised by the backend are surfaced to the employee with clear and consistent messaging. |  |  |  |  | IN-04, BE-10, FE-07 | Integration Team | Reimbursement Module
IN-06 - Attachment upload end-to-end wiring | Connect the attachment upload experience to the backend attachment capability and confirm a bill can be attached to a request. |  |  |  |  | IN-04, BE-11, FE-09 | Integration Team | Reimbursement Module
IN-19 - Deduction listing end-to-end wiring | Connect the deduction list screen to the backend listing capability and confirm summary values are accurate. |  |  |  |  | BE-26, FE-26 | Integration Team | Deduction Module
IN-08 - Employee reimbursement history end-to-end wiring | Connect the employee history screen to the backend retrieval capability and confirm status and amounts display correctly. |  |  |  |  | BE-12, FE-12 | Integration Team | Reimbursement Module
IN-17 - Employee search end-to-end wiring for deductions | Connect employee search on the deduction screen to the backend lookup and confirm only active employees are returned. |  |  |  |  | IN-16, BE-25, FE-23 | Integration Team | Deduction Module
IN-18 - Deduction validation handling end-to-end | Confirm validation failures raised by the backend are surfaced correctly on the deduction screen. |  |  |  |  | IN-16, BE-24, FE-24 | Integration Team | Deduction Module
IN-07 - Attachment retrieval and removal end-to-end | Confirm an attached bill can be viewed and removed end to end, with correct behaviour once a request has been submitted. |  |  |  |  | IN-06, FE-10 | Integration Team | Reimbursement Module
IN-09 - Administrator pending list end-to-end wiring | Connect the administrator pending list to the backend retrieval capability and confirm only relevant requests are listed. |  |  |  |  | BE-13, FE-15 | Integration Team | Reimbursement Module
IN-20 - Deduction update end-to-end wiring | Connect the deduction edit experience to the backend update capability and confirm eligibility rules are respected. |  |  |  |  | IN-19, BE-27, FE-28 | Integration Team | Deduction Module
IN-22 - Deduction filter end-to-end wiring | Connect the deduction filter controls to the backend filtering capability and confirm results are accurate. |  |  |  |  | BE-29, FE-27 | Integration Team | Deduction Module
IN-27 - Attachment storage integration verification | Verify supporting bills are stored and retrieved reliably through the existing document storage integration. |  |  |  |  | IN-07 | Integration Team | Reimbursement Module
IN-10 - Reimbursement detail review end-to-end wiring | Connect the review screen to the backend detail capability and confirm attachments and remarks are presented correctly. |  |  |  |  | IN-09, BE-14, FE-17 | Integration Team | Reimbursement Module
IN-15 - Reimbursement search and filter end-to-end wiring | Connect the administrator search and filter controls to the backend filtering capability and confirm results are accurate. |  |  |  |  | BE-19, FE-16 | Integration Team | Reimbursement Module
IN-24 - Deduction history reporting end-to-end wiring | Connect the deduction history view to the backend reporting data and confirm the values reconcile with individual records. |  |  |  |  | BE-31, FE-30 | Integration Team | Deduction Module
IN-21 - Deduction removal end-to-end wiring | Connect the removal action end to end and confirm history is retained after a deduction is withdrawn. |  |  |  |  | IN-20, BE-28, FE-29 | Integration Team | Deduction Module
IN-11 - Approval action end-to-end wiring | Connect the approval action end to end and confirm the resulting status and approver details are recorded and displayed. |  |  |  |  | IN-10, BE-15, FE-18 | Integration Team | Reimbursement Module
IN-13 - Rejection action end-to-end wiring | Connect the rejection action end to end and confirm the reason is captured and visible to the employee. |  |  |  |  | IN-10, BE-17, FE-20 | Integration Team | Reimbursement Module
IN-23 - Deduction status behaviour end-to-end | Confirm deduction status transitions behave consistently between the administrator screens and the stored record. |  |  |  |  | IN-20, BE-30 | Integration Team | Deduction Module
IN-25 - Organization data isolation verification | Verify across both modules that records raised in one organization are never visible to another, using multi-organization test accounts. |  |  |  |  | BE-32, IN-09, IN-19 | Integration Team | Common Platform Activities
IN-12 - Partial approval end-to-end wiring | Confirm an approved amount lower than the requested amount is captured, stored and displayed correctly across both portals. |  |  |  |  | IN-11, BE-16, FE-19 | Integration Team | Reimbursement Module
IN-26 - Portal access boundary verification | Verify employee-facing and administrator-facing capabilities are reachable only from the intended portal for both modules. |  |  |  |  | BE-33, FE-31, IN-25 | Integration Team | Common Platform Activities
IN-14 - Remarks management end-to-end wiring | Confirm approver remarks are captured, revised and displayed correctly without affecting the approved amount. |  |  |  |  | IN-12, IN-13, BE-18, FE-21 | Integration Team | Reimbursement Module
IN-28 - Existing payroll behaviour impact check | Confirm the introduction of both modules has not altered existing pay run, payslip or statutory behaviour. |  |  |  |  | IN-14, IN-24 | Integration Team | Common Platform Activities
IN-29 - Non-production environment deployment | Deploy the integrated modules to the non-production environment and confirm the environment is stable for test execution. |  |  |  |  | IN-26, IN-28 | Integration Team | Common Platform Activities
IN-30 - Integrated smoke verification | Run an agreed short smoke pass across both modules after deployment to confirm the build is fit for formal testing. |  |  |  |  | IN-29 | Integration Team | Common Platform Activities
IN-32 - Integration documentation | Record the integration sequence, environment configuration and verification outcomes for handover and future reference. |  |  |  |  | IN-30 | Integration Team | Common Platform Activities
PM-12 - Milestone review - integration complete | Review and confirm both modules are integrated end to end and the build is fit for formal testing. |  |  |  |  | IN-30 | Project Team | Common Platform Activities
PHASE 6. Defect Resolution
IN-31 - Integration issue resolution support | Support the backend and frontend teams in diagnosing and closing integration issues raised during the integration phase. |  |  |  |  | IN-30 | Integration Team | Common Platform Activities
PM-15 - Delivery risk review | Reassess delivery risk against the remaining plan and agree mitigation or scope adjustment with the business owner. |  |  |  |  | PM-14 | Project Team | Common Platform Activities
PHASE 7. UAT
IN-33 - UAT environment preparation | Prepare and refresh the environment used for user acceptance testing, including the agreed test data set for both modules. |  |  |  |  | IN-30 | Integration Team | Common Platform Activities
IN-34 - Integration UAT support | Support user acceptance testing by resolving environment issues and coordinating fixes across teams. |  |  |  |  | IN-33 | Integration Team | Common Platform Activities
PHASE 8. Release & Closure
IN-35 - Production deployment readiness review | Confirm deployment steps, rollback approach and post-deployment checks are agreed and documented before release. |  |  |  |  | IN-34 | Integration Team | Common Platform Activities
PM-17 - Go-live readiness review | Review release readiness across development, testing, environments and business sign-off, and record the go or no-go decision. |  |  |  |  | QA-38, IN-35 | Project Team | Common Platform Activities
PM-18 - Release note preparation | Prepare the release note summarising delivered functionality, known limitations and deferred items for both modules. |  |  |  |  | PM-17 | Project Team | Common Platform Activities
PM-19 - Production release and delivery | Complete the production release of both modules and confirm delivery to the business owner. |  |  |  |  | PM-17 | Project Team | Common Platform Activities
TOTAL | 41 tasks

## Testing
Payroll Management System - Project Plan
Workstream: Quality Assurance ¦ Owners: QA Team, Project Team ¦ Functional, validation, service-level, security, regression, UAT and closure
Tasks: 44 ¦ Reporting date: 10-Aug-2026 ¦ Delivery: 21-Aug-2026
Task/Activity | Activity Details | Status | No of Days | Start | Finish | Dependency | Owner | Scope
PHASE 2. Design & Planning
QA-01 - Test strategy definition | Define the overall test approach for both modules, covering test levels, entry and exit criteria, environments and defect management process. |  |  |  |  | BE-04, FE-04 | QA Team | Common Platform Activities
QA-02 - Test scenario identification - Reimbursement | Identify the full set of test scenarios for reimbursement submission, review, approval, partial approval and rejection. |  |  |  |  | QA-01 | QA Team | Reimbursement Module
QA-03 - Test scenario identification - Deduction | Identify the full set of test scenarios for deduction creation, listing, update, removal and history. |  |  |  |  | QA-01 | QA Team | Deduction Module
QA-04 - Test case preparation - Reimbursement employee portal | Prepare detailed test cases for the request form, attachment handling, validation messaging and reimbursement history. |  |  |  |  | QA-02 | QA Team | Reimbursement Module
QA-05 - Test case preparation - Reimbursement admin portal | Prepare detailed test cases for the pending list, request detail, approval, partial approval, rejection and remarks. |  |  |  |  | QA-02 | QA Team | Reimbursement Module
QA-06 - Test case preparation - Deduction admin portal | Prepare detailed test cases for deduction creation, employee search, listing, update, removal and filtering. |  |  |  |  | QA-03 | QA Team | Deduction Module
QA-07 - Validation test case preparation | Prepare negative and boundary test cases covering mandatory fields, amount limits, date rules and duplicate prevention for both modules. |  |  |  |  | QA-04, QA-05, QA-06 | QA Team | Common Platform Activities
QA-10 - Regression test scope definition | Identify the existing payroll functionality that must be regression tested, prioritised by risk of impact. |  |  |  |  | QA-01 | QA Team | Common Platform Activities
QA-08 - Security and access test case preparation | Prepare test cases covering organization data isolation, portal boundaries and unauthorised access attempts for both modules. |  |  |  |  | QA-07 | QA Team | Common Platform Activities
QA-09 - Service-level test case preparation | Prepare service-level test cases covering successful and failing requests, error handling and access restrictions for both modules. |  |  |  |  | QA-07 | QA Team | Common Platform Activities
QA-11 - Test data preparation | Prepare the test data set covering multiple organizations, employees, reimbursement types and deduction reasons. |  |  |  |  | QA-08 | QA Team | Common Platform Activities
QA-12 - Test case review and sign-off | Review all prepared test cases with the business owner and technical leads and obtain approval to proceed. |  |  |  |  | QA-09, QA-11 | Project Team | Common Platform Activities
QA-13 - Test environment verification | Confirm the test environment is correctly configured and the agreed test data has been loaded successfully. |  |  |  |  | QA-12, IN-02 | QA Team | Common Platform Activities
PHASE 5. Testing
QA-14 - Functional testing - Reimbursement request submission | Execute test cases covering employee reimbursement submission across all reimbursement types. |  |  |  |  | IN-05, QA-13 | QA Team | Reimbursement Module
QA-15 - Functional testing - Attachment management | Execute test cases covering attachment upload, preview, removal and permitted file handling. |  |  |  |  | IN-07, QA-13 | QA Team | Reimbursement Module
QA-22 - Functional testing - Deduction creation | Execute test cases covering deduction creation across all in-scope reason categories. |  |  |  |  | IN-18, QA-13 | QA Team | Deduction Module
QA-23 - Functional testing - Employee search for deductions | Execute test cases covering employee lookup behaviour and restriction to active employees. |  |  |  |  | IN-17, QA-13 | QA Team | Deduction Module
QA-24 - Functional testing - Deduction listing and filtering | Execute test cases covering the deduction list, summary values and all filter combinations. |  |  |  |  | IN-19, IN-22 | QA Team | Deduction Module
QA-16 - Functional testing - Employee reimbursement history | Execute test cases covering history display, status presentation and employee-side filtering. |  |  |  |  | IN-08, QA-13 | QA Team | Reimbursement Module
QA-17 - Functional testing - Pending reimbursement list | Execute test cases covering the administrator pending list content, ordering and summary values. |  |  |  |  | IN-09, QA-13 | QA Team | Reimbursement Module
QA-18 - Functional testing - Reimbursement approval workflow | Execute test cases covering full approval, resulting status and recorded approver details. |  |  |  |  | IN-11, QA-13 | QA Team | Reimbursement Module
QA-20 - Functional testing - Reimbursement rejection workflow | Execute test cases covering rejection, mandatory reason capture and employee visibility of the outcome. |  |  |  |  | IN-13, QA-13 | QA Team | Reimbursement Module
QA-25 - Functional testing - Deduction update and removal | Execute test cases covering amendment of an existing deduction, eligibility rules and withdrawal behaviour. |  |  |  |  | IN-21, QA-24 | QA Team | Deduction Module
QA-26 - Functional testing - Deduction history and status | Execute test cases covering deduction history reporting and status transitions. |  |  |  |  | IN-23, IN-24 | QA Team | Deduction Module
QA-19 - Functional testing - Partial approval scenarios | Execute test cases covering approved amounts lower than requested, including the stated example of 5000 requested against 3000 approved. |  |  |  |  | IN-12, QA-18 | QA Team | Reimbursement Module
QA-21 - Functional testing - Remarks and search | Execute test cases covering remarks capture and administrator search and filtering of reimbursement records. |  |  |  |  | IN-14, IN-15 | QA Team | Reimbursement Module
QA-27 - Validation testing - both modules | Execute negative and boundary test cases covering mandatory fields, amount limits, date rules and duplicate prevention. |  |  |  |  | QA-19, QA-25 | QA Team | Common Platform Activities
QA-30 - Security and access testing | Execute test cases covering organization data isolation, portal access boundaries and unauthorised access attempts. |  |  |  |  | IN-26, QA-08 | QA Team | Common Platform Activities
QA-28 - Defect logging and triage - cycle 1 | Log all defects from the first test cycle, triage with the development leads and agree severity and fix priority. |  |  |  |  | QA-27 | QA Team | Common Platform Activities
QA-29 - Service-level testing - both modules | Execute service-level test cases covering successful requests, error responses and access restrictions. |  |  |  |  | IN-30, QA-09 | QA Team | Common Platform Activities
QA-31 - Retesting of resolved defects - cycle 1 | Retest all defects resolved in the first fix cycle and confirm closure or reopen with additional detail. |  |  |  |  | BE-38, FE-36 | QA Team | Common Platform Activities
QA-32 - Regression testing - existing payroll functionality | Execute the agreed regression suite to confirm existing pay run, payslip and statutory behaviour is unaffected. |  |  |  |  | QA-31, IN-28 | QA Team | Common Platform Activities
QA-33 - Retesting of resolved defects - cycle 2 | Retest defects resolved in the second fix cycle and confirm no new issues have been introduced. |  |  |  |  | BE-39, FE-37 | QA Team | Common Platform Activities
QA-34 - Test cycle closure and readiness report | Close the test cycle, publish results, outstanding defects and a recommendation on readiness for user acceptance testing. |  |  |  |  | QA-32, QA-33 | QA Team | Common Platform Activities
PM-13 - Milestone review - testing complete | Review test results, outstanding defects and residual risk, and confirm readiness for user acceptance testing. |  |  |  |  | QA-34 | Project Team | Common Platform Activities
PHASE 6. Defect Resolution
PM-14 - Defect trend monitoring | Monitor defect volumes, ageing and closure rates across test cycles and escalate where closure is at risk. |  |  |  |  | QA-28 | Project Team | Common Platform Activities
PHASE 7. UAT
QA-35 - UAT test case handover and walkthrough | Hand over the acceptance scenarios to the business users and walk them through the agreed test flows for both modules. |  |  |  |  | QA-34 | QA Team | Common Platform Activities
PM-16 - UAT coordination | Coordinate user acceptance testing scheduling, participants and daily progress reviews with the business owner. |  |  |  |  | QA-35 | Project Team | Common Platform Activities
QA-36 - UAT execution support | Support business users throughout user acceptance testing, capture observations and route them to the correct team. |  |  |  |  | QA-35, IN-33 | QA Team | Common Platform Activities
QA-37 - UAT defect coordination and closure | Track defects raised during user acceptance testing through to resolution and confirm closure with the business owner. |  |  |  |  | QA-36 | QA Team | Common Platform Activities
QA-38 - UAT sign-off | Obtain formal user acceptance sign-off from the business owner for both modules. |  |  |  |  | QA-37 | Project Team | Common Platform Activities
PHASE 8. Release & Closure
QA-39 - Test summary report | Publish the final test summary covering coverage, execution results, defect statistics and residual risk. |  |  |  |  | QA-37 | QA Team | Common Platform Activities
QA-40 - Production release verification | Execute the agreed post-deployment verification pass on the production environment and confirm both modules are functioning. |  |  |  |  | QA-38, IN-35 | QA Team | Common Platform Activities
PM-20 - Project closure and lessons learned | Close the project, capture lessons learned and hand over outstanding items to the support and future release backlog. |  |  |  |  | PM-19 | Project Team | Common Platform Activities
TOTAL | 44 tasks

## Project Summary
Payroll Management System - Project Summary
Reimbursement Management Module and Employee Deduction Management Module ¦ Reporting date 10-Aug-2026 ¦ Delivery date 21-Aug-2026
1. Headline Figures
Measure | Value
Total tasks in plan | 176
Total estimated effort (person-days) | 441
Modules in scope | 2
Delivery teams involved | 4
Project start | 2026-08-10
Planned completion | 2026-08-21
Committed delivery date | 2026-08-21
Working days remaining to delivery | 9
2. Tasks by Module (Scope)
Scope / Module | Tasks
Reimbursement Module | 59
Deduction Module | 39
Common Platform Activities | 78
TOTAL | 176
5. Status Position as at Reporting Date
Status | Tasks
Completed | 160
In Progress | 3
Planned | 12
Blocked | 1
TOTAL | 176
6. Planned Timeline by Phase
Phase | Tasks
1. Requirements & Analysis | 11
2. Design & Planning | 25
3. Development | 63
4. Integration | 29
5. Testing | 22
6. Defect Resolution | 8
7. UAT | 9
8. Release & Closure | 9
8. Delivery
Item | Detail
Final delivery date | 2026-08-21
Delivery scope | Reimbursement Management Module and Employee Deduction Management Module
Acceptance basis | Business sign-off at UAT (QA-38) and go-live readiness approval (PM-17)
Deferred to a future release | Consumption of approved reimbursement and deduction amounts within payroll processing (assessed under BE-40)
Status of plan | Baselined
9. Notes and Assumptions
- Effort is stated in person-days. Durations are working days and exclude weekends and public holidays.
- Dependencies name predecessor task identifiers. A task begins only after every listed predecessor is complete.
- Status is reported as at the reporting date shown above and is refreshed at each weekly status review.
- Both modules record and approve amounts only. Applying those amounts inside a payroll run is out of scope for this release.
- Tasks marked Blocked are awaiting a business or technical decision and are excluded from the critical path to delivery.
- Parallel work across teams assumes the agreed team allocation in PM-04 is held for the full delivery window.